AZFA Conference Host Timeline

32 months out

- Apply for conference

24 months out

- Awarded conference

18 months out

- Present hotel contract to officers at AZFA Mid-year Meeting

16 months out

- Sign contract with host hotel

- Begin working with Programs & Education to develop agenda

12 months out

- Present preliminary agenda to officers at Board Meeting

- Recruit vendors & sponsors

10 months out

- Finalize contracts for attendee transportation needs

6 months out

- Present 70% agenda to officers at AZFA Mid-year Meeting

- Online registration system in place

- Catering contracts in place

5 months out

- 95% agenda posted on the web site

- Ready to receive registrations

- Ready for vendor registrations, exhibit hall lay out, receiving, etc.

3 months out

- Final agenda posted on the web site