AZFA Annual Conference Preparations To-Do List

Agenda

- Determine printing deadline – Usually need at least 48 hours in advance

- Finalize presentation schedule with Program & Education Committee

- Secure Keynote/Welcome speaker

- Finalize hotel breakout room assignments

- Send Web version to AZFA webmaster at least 6 weeks before conference to post

- E-mail blast of Web version ASAP to all AZFA

- Collect vendor/sponsor logos

- Design cover

- Include driving directions for airport, hotel, host facility, and pre- and post-conference tours

- Finalize agenda Word document or PDF

- Print agenda

- Save digital copy onto giveaway thumb drives in advance (if providing drives in welcome bag)

Sponsorships – Program printing, meals, transportation, welcome bags, etc.

- Determine sponsorship levels ASAP based on budget and anticipated conference costs

- Request sponsors from previous conference contributors as well as new and local vendors

- Presenting sponsor(s)

- Platinum sponsors

- Gold sponsors

- Silver sponsors

- Bronze sponsors

- In-kind sponsorships: various tools/gifts for silent auction and tool raffle, items for welcome bags, coupons from local vendors and restaurants

Welcome Bags

- Tote or backpack with conference logo (Waterlife sponsor item for past several years)

- Pens and notepads – donated

- Coupons and tourist information – request from Human Resources or Marketing

- Thumb drives (pre-loaded with program and sponsor info)?

- Reusable beverage container with logo

- Compile giveaway bags – host facility volunteers

- Deliver welcome bags to hotel

Transportation

- Secure contract for buses to pre- and post-conference tour venues, hotel, and host facility

- Arrange backup transport for stragglers or early departures – host facility vehicle?

- Adjust transportation contract depending on final registration numbers

- Assign volunteers to take attendance on buses for each outing

- Print attendee lists based on final registration for volunteers to check during loading

Pre-Conference Tour

- Select and confirm tour facility ASAP; make contract arrangements if needed

- Provide facility information and tour details for conference website/e-mail updates

- Arrange for boxed lunch or catering

- Print list of attendees registered for tour to check in on buses

- Load lunches/beverages on bus if needed

- Send thank-you letter to tour facility afterwards

Ice Breaker

- Select and reserve ice breaker facility ASAP

- Arrange catering contract and rentals if needed (tables and chairs)

- Select menu, tableware, decorations, etc.

- Request check in advance for deposit if needed

- Arrange audio visual/IT equipment needs

- Schedule welcome speaker (from host facility)

Hotel

- Sign contract for rooms and group rate ASAP

- Meet with catering and AV contacts for meals and IT needs: coffee breaks, lunches, cash bar, closing banquet, projectors, screens (use host facility equipment as much as possible to reduce costs)

- Determine meeting room, banquet, and breakout room assignments

- Select hospitality suite

- Finalize food and beverage contract

- Finalize AV contract

- Inventory IT needs (computer, printer, projectors)

- Determine vendor contact for load-in and equipment delivery

- Coordinate vendor table set up needs

- Deliver host facility IT equipment to hotel – host facility staff and volunteers

- Set up, stock, and monitor hospitality suite – host facility staff and volunteers

- Guard host facility IT equipment throughout conference – hotel security and/or host facility staff

- Set up and monitor IT equipment during presentations – host facility IT staff

Zoo Day

- Reserve banquet/meeting space ASAP at host facility

- Determine welcome speaker and opening remarks

- On-screen presentation of day’s schedule – host facility IT staff

- Arrange behind-the-scenes tours with animal departments

- Arrange tours of maintenance shops, life support and aquatics facilities, new construction projects, etc.

- Request catering from food services department: coffee, juice, light pastries for morning; lunch; cold beverages for afternoon

- Request photographer for group photo through Marketing department

- Secure equipment rental for training/workshops if needed: forklift, boom lift, etc.

- Set up training and workshops

- Arrange for docents or Education department staff to serve as guides throughout day

- Provide maps for conference attendees

- Assign staff to monitor banquet room/conference base all day for questions and assistance

- Hang conference banner at host facility

Vendors & Sponsors

- Maintain updated records of vendor registrations

- Send out confirmation letters when payments received

- Request contact information and digital copies of vendor logos for program

- Create and distribute vendor information packet (load-in and equipment delivery)

- Make vendor table assignments according to sponsor levels, registration date

- Make and print vendor raffle cards

- Provide vendor raffle prize (donated tool?)

- Meet vendors during load-in and assist as needed

- Assist vendors with break down and departure as needed

- Send thank-you letters and follow-up survey after the conference

Registration

- Maintain updated records of online and mail-in registrations

- Request use of and training on wireless credit card readers if available from host facility

- Request cash box and money handling materials from host facility

- Print name badges, including blank spares for attendees who register on arrival

- Assemble name badge holders and lanyards

- Set up and monitor check-in table/info booth throughout conference – host facility staff and volunteers

- Print labels and log sheet for silent auction items

- Collect, record, and label silent auction items – host facility staff and volunteers

- Transport silent auction items to hospitality suite (or other secure location) – host facility staff

- Take last-minute sign-ups and payment for pre- and post-conference tours – host facility staff

- Print or use laptop with registration spreadsheet to check in attendees and collect fees if needed

- Collect thumb drives from presenters and load presentations onto laptop in advance

- Print sign-up sheets if needed for workshops/training

- Print and distribute certificates of completion for applicable workshops/training

Silent Auction and Closing Banquet

- If possible, secure sponsor or use host facility account for shipping auction items

- Request shipping boxes from USPS and extra packing materials from host facility warehouse

- Request silent auction item donations

- Print silent auction item descriptions

- Print silent auction bid sheets

- Set up silent auction – host facility staff and AZFA volunteers

- Assist auction winners with packing/shipping items – host facility staff and AZFA volunteers

- Set up lanyard and name badge holder collection box for reuse at next conference

- Distribute copies of group photo

Post-Conference Tour

- Select and confirm tour facility ASAP; make contract arrangements if needed

- Provide facility information and tour details for conference website/e-mail updates

- Arrange for boxed lunch or catering

- Print list of attendees registered for tour to check in on buses

- Load lunches/beverages on bus if needed

- Send thank-you letter to tour facility afterwards

Signage and Printouts

- Member registration sign-in sheets

- Vendor & sponsor registration sign-in sheets

- Pre- and post-conference tour late registration sheets

- Bus check-in attendance sheets (pre- and post- tours and Zoo Day)

- Design and fabricate all conference signs for tables and easels: vendors, sponsorships, auction, raffles, info, tour and workshop sign-ups, elections, welcome

- Provide tabletop easels for signs if needed (Displays2Go.com is affordable source)

- Print workshop and session sign-up sheets

- Print meeting minutes and election ballots for business meeting

- Print committee sign-up sheets

Miscellaneous

- Request event publication in AZA Connect calendar (Tim Lewthwaite at TLewthwaite@aza.org)

- Seek coupons and promotions from local businesses and restaurants

- Design and order banner with presentation sponsor logo if needed

- Coordinate volunteer schedules and duties

- Coordinate with photographer and arrange for group photo printing

- Thank-yous for all volunteers and staff helpers

Financial

- Conference budget

- Request cash bag and change for registration table

- Coordinate AZFA membership payments and conference fee reimbursements with AZFA Treasurer

- Reconcile host facility expenditures and AZFA reimbursements

- Request final check payments for hotel, catering, and transportation contracts as needed

- Collect outstanding registration/vendor/sponsorship payments if needed

Items to Deliver to Hotel

- Welcome bags

- Programs

- Name badges and lanyards (and collection box for reuse after conference)

- Registration records

- Hotel contract, catering information, presentation room assignments, etc.

- IT equipment (laptops, printer, projector, extra thumb drives)

- Silent auction items

- Tool raffle items

- Conference banner

- Signs and easels

- Cash box and money handling materials (including credit card readers if available)

- Extra printing materials: paper, labels, registration forms, etc.

- Extra office supplies: pens, markers, staplers, tape, rubber bands, etc.

- Shipping and packing supplies